## Evidence Tracker
FCRM Risk Assessment FY2025 — Evidence Tracker
Maps each process step to required evidence, owner, location, and status ¦ System of Record: SharePoint + Jira ¦ Last Updated: April 2026
Process | Sub-Process / Step | Step # | Owner | Expected Evidence / Artifact | Artifact Name / File | SharePoint / Jira Location | Status | Jira Ticket(s) | Last Verified | Verified By | Gap / Notes | Priority | Due Date | Linked SOP | Audit Ready?
Delivery Process | Intake Request | 0 | Amandeep | Jira ticket created, CDE list, initial review record |  |  | Missing | [6 empty] | 01 - Delivery Process SOP v1.2 | No
| Scope / Requirement Def. | 1 | Amandeep | Scope & Requirements Document, SOW reference |  |  | Missing | [6 empty] | 01 - Delivery Process SOP v1.2 | No
| Data Acquisition | 2 | Amandeep | Extraction scripts, extracted dataset files in CA AZ |  |  | Missing | [6 empty] | 01 - Delivery Process SOP v1.2 | No
| Logic Development (Build) | 3 | Karthik | Python-SQL queries in Git, Jira ticket in BUILD IN PROGRESS |  |  | Missing | [6 empty] | 01 - Delivery Process SOP v1.2 | No
| Technical Specifications | 4 | Karthik | Tech spec doc, transformation logic, field-level mapping |  |  | Missing | [6 empty] | 01 - Delivery Process SOP v1.2 | No
| Output Validation | 5 | Karthik | Output validation report, reconciliation results |  |  | Missing | [6 empty] | 01 - Delivery Process SOP v1.2 | No
| Approval | 6 | Karthik | Jira ticket in PO CONCURRENCE → PO APPROVED state |  |  | Missing | [6 empty] | 01 - Delivery Process SOP v1.2 | No
| Deployment | 7 | Karthik | Deployment log, release record |  |  | Missing | [6 empty] | 01 - Delivery Process SOP v1.2 | No
| Delivery / Document | 8 | Karthik | Final output files, delivery confirmation |  |  | Missing | [6 empty] | 01 - Delivery Process SOP v1.2 | No
Validation & QA | Validation Planning | 1 | Priyanshi | Validation Plan Document, Risk Assessment Matrix |  |  | Missing | [6 empty] | 02 - QA & Governance SOP v2.1 | No
| Data Quality Checks | 2 | Priyanshi | DQ check results (completeness, accuracy, consistency, uniqueness, timeliness) |  |  | Missing | [6 empty] | 02 - QA & Governance SOP v2.1 | No
| Reconciliation | 3 | Priyanshi | Reconciliation report, variance analysis log |  |  | Missing | [6 empty] | 02 - QA & Governance SOP v2.1 | No
| Reasonability Analysis | 4 | Priyanshi | Trend analysis output, outlier detection log, threshold validation |  |  | Missing | [6 empty] | 02 - QA & Governance SOP v2.1 | No
| Peer Review | 5 | Sujai | Peer review sign-off, review comments log |  |  | Missing | [6 empty] | 02 - QA & Governance SOP v2.1 | No
| Output Verification | 6 | Sujai | Output verification report, format compliance log |  |  | Missing | [6 empty] | 02 - QA & Governance SOP v2.1 | No
| Issue Logging | 7 | Sujai | RAID log entry, Jira BLOCKED ticket with issue detail |  |  | Missing | [6 empty] | 02 - QA & Governance SOP v2.1 | No
| Sign-Off & Approval | 8 | Sujai | Signed approval record (AVP+), final validation report |  |  | Missing | [6 empty] | 02 - QA & Governance SOP v2.1 | No
Data Sourcing & Lineage | Source Identification | 1 | Hua | Master_Data_source_FY2025.xlsx, source identification log |  |  | Missing | [6 empty] | 03 - Data Sourcing & Lineage v1.0 | No
| Access Enablement | 2 | Hua | PIA approval records, access request forms, access approval log |  |  | Missing | [6 empty] | 03 - Data Sourcing & Lineage v1.0 | No
| Data Extraction | 3 | Hua | Extracted dataset files (.csv/.parquet), extraction scripts, extraction validation report |  |  | Missing | [6 empty] | 03 - Data Sourcing & Lineage v1.0 | No
| Data Understanding | 4 | Subham | Data profiling reports, data dictionary / metadata documentation |  |  | Missing | [6 empty] | 03 - Data Sourcing & Lineage v1.0 | No
| Lineage Documentation | 5 | Subham | Data lineage diagrams, transformation logic documentation, lineage register |  |  | Missing | [6 empty] | 03 - Data Sourcing & Lineage v1.0 | No
| Refresh Management | 6 | Raghul | Refresh activity log, refresh validation reports |  |  | Missing | [6 empty] | 03 - Data Sourcing & Lineage v1.0 | No
| Data Retention | 7 | Raghul | Data retention statement, retention policy reference |  |  | Missing | [6 empty] | 03 - Data Sourcing & Lineage v1.0 | No
Governance & Issue Mgmt | Decision Logging | 1 | Patty | Jira ticket in BUSINESS LOGIC DESIGN DEF state with decision notes |  |  | Missing | [6 empty] | 04 - Governance SOP | No
| Assumption Tracking | 2 | Patty | Jira ticket in METRIC DEFINITION CLARIFICATION state, assumption log |  |  | Missing | [6 empty] | 04 - Governance SOP | No
| Issue Logging | 3 | Patty | RAID log entry, Jira BLOCKED ticket |  |  | Missing | [6 empty] | 04 - Governance SOP | No
| Severity Assessment | 4 | Patty | Severity classification (P1/P2) in RAID log |  |  | Missing | [6 empty] | 04 - Governance SOP | No
| Escalation Pathways | 5 | Tom | Escalation record, Jira comments showing escalation chain |  |  | Missing | [6 empty] | 04 - Governance SOP | No
| Resolution & Unblocking | 6 | Tom | RAID log closure, Jira state transition off BLOCKED |  |  | Missing | [6 empty] | 04 - Governance SOP | No
| Risk Acceptance | 7 | Tom | Risk acceptance record, metric transitioned to NOT AVAILABLE |  |  | Missing | [6 empty] | 04 - Governance SOP | No
| Decommissioning | 8 | Tom | Jira state: NO LONGER REQUIRED or NOT APPLICABLE |  |  | Missing | [6 empty] | 04 - Governance SOP | No
Access Control & Security | PIA Initiation | 1 | Hua | PIA initiated for each data source requiring personal/sensitive data |  |  | Missing | [6 empty] | 05 - Access Control SOP | No
| Access Request | 2 | Hua | Access request forms submitted per system |  |  | Missing | [6 empty] | 05 - Access Control SOP | No
| Access Approval | 3 | Hua | Access approval records, confirmation emails |  |  | Missing | [6 empty] | 05 - Access Control SOP | No
| DEV vs PROD Separation | 4 | TBD | Evidence of environment separation, access matrix |  |  | Missing | [6 empty] | 05 - Access Control SOP | No
| Periodic Review | 5 | TBD | Periodic access review log, attestation records |  |  | Missing | [6 empty] | 05 - Access Control SOP | No
Change Management | Change Request | 1 | TBD | Jira change ticket raised before logic modification |  |  | Missing | [6 empty] | 06 - Change Management SOP | No
| Impact Assessment | 2 | TBD | Impact assessment notes in Jira ticket |  |  | Missing | [6 empty] | 06 - Change Management SOP | No
| Approval | 3 | TBD | Approval sign-off on change ticket |  |  | Missing | [6 empty] | 06 - Change Management SOP | No
| Version Control | 4 | TBD | Git commit history, PR / merge record |  |  | Missing | [6 empty] | 06 - Change Management SOP | No
| Deployment | 5 | TBD | Deployment log, release notes |  |  | Missing | [6 empty] | 06 - Change Management SOP | No
| Scope Change Logging | 6 | Richard Ng | SOW weekly change log (v1.32), scope change entry |  |  | Missing | [6 empty] | 06 - Change Management SOP | No

## Summary Dashboard
Evidence Tracker — Summary Dashboard
Counts update automatically as you fill in the Evidence Tracker sheet
Process Area | Total Steps | Exists | Partial | Missing | % Complete
Delivery Process | 9
Validation & QA | 8
Data Sourcing & Lineage | 7
Governance & Issue Mgmt | 8
Access Control & Security | 5
Change Management | 6
TOTAL
KEY PROJECT STATS (FY2025)
Total Work Packages |  |  |  | 4
Total Metric Definitions |  |  |  | 86
Total Assessable Units (AUs) |  |  |  | 35
Total Metric Instances |  |  |  | 2,240
Jira — BUILD COMPLETE |  |  |  | 754
Jira — BLOCKED (active) |  |  |  | 49
RAID Log Items |  |  |  | 137
Rahona Data Sources |  |  |  | 20
ADIDO Data Sources |  |  |  | 73

## Instructions
HOW TO USE THIS EVIDENCE TRACKER
PURPOSE | This tracker maps every process step to its required evidence artifact. Use it to identify gaps, track progress, and demonstrate audit readiness.
STATUS COLUMN (H) | Select from: Exists / Partial / Missing / N/A • Exists = artifact is complete and located • Partial = artifact exists but is incomplete • Missing = artifact not yet produced • N/A = step not applicable to this cycle
ARTIFACT NAME (F) | Enter the actual filename of the evidence (e.g., 'Reconciliation_Report_WP01_Apr2026.xlsx')
LOCATION (G) | Paste the full SharePoint URL or Jira ticket ID where the evidence lives
JIRA TICKETS (I) | Enter comma-separated Jira ticket IDs that serve as evidence for this step (e.g., FY25DATA-359, FY25DATA-401)
PRIORITY (M) | High = must exist for audit / Medium = important but not blocking / Low = nice to have
AUDIT READY (P) | Yes = evidence is complete, located, and verified In Progress = being worked on No = not started
SUMMARY DASHBOARD | The Summary Dashboard sheet auto-calculates completion % by process area as you update the Status column.
SHAREPOINT STRUCTURE | 00 - Audit Navigation 01 - Delivery Process 02 - Validation & QA 03 - Data Sourcing & Lineage 04 - Governance & Issue Mgmt 05 - Access Control & Security 06 - Change Management 07 - Process Flow Diagrams 08 - Archive
OWNER | FCRM Enterprise Risk Assessment Reporting Team ¦ April 2026 ¦ Internal