## Out of Scope Tracker
FY25 RA — Out of Scope / NA / Deferred Items Tracking
Records FY2025 risk-assessment items determined out of scope, not applicable, or deferred — the decision, the reason, and the sign-off. Workflow: brainstorm with developers → clean list → review with Andrew/ERA → write into SOW + specs.
ID | Item / Topic | Work Package / Metric / AU | What was requested / discussed | Disposition | Reason Category | Reason Detail | Decided By | Decision Date | Sign-off By | Sign-off Date | Source / Evidence | FY26 Opportunity / Carry-forward | Status | Notes
OOS-001 | Transaction data scope | Inherent Risk / Transaction monitoring | Which transaction types are in scope — wires, cross-border — and sender vs receiver treatment. |  |  | Ambiguity over transaction scope raised during FY25; ~half of expected items may relate to transaction data. |  |  |  |  | Diane transaction-data email thread; FY25 RA discussions |  | Open

## Reference
Disposition — what was decided
Out of Scope | Determined not part of the FY2025 risk-assessment scope.
Not Applicable | Considered but does not apply to this assessment.
Deferred | In scope in principle but not completed this cycle; carried to a future cycle.
Reason Category — why
Data unavailable | Required data could not be obtained.
Data location unknown | Could not determine where the data resides.
Requirement unclear/undefined | The requirement was not clearly defined.
Descoped vs FY24 | Changed from the prior year; deliberately removed.
Resource capacity | Insufficient team capacity.
Runway/time | Insufficient time in the cycle.
Other | Reason not covered above — explain in Reason Detail.
Workflow
1. Brainstorm | Gather items with all developers (standup or dedicated session); pull RAID-log items as pre-reads.
2. Clean list | Consolidate item + reason + opportunity; assign IDs.
3. Review | Walk the list with Andrew / ERA team; obtain sign-off.
4. Record | Write into the SOW / scope document and fold relevant items into the specs.
Source
Meeting | FY25 Documentation on RA Out of Scope/NA/Deferred Items Tracking — 2026-06-15.