TD Bank Group · FCRM Enterprise Risk Assessment Reporting Team Governance, Decision & Issue Management ML/TF and Sanctions Risk Assessment · FY2025 · MCC Team Version 1.0 · June 2026 · Internal · 1LOD / 2LOD / 3LOD and Regulatory Reviewers

| Attribute | Detail |
| --- | --- |
| Document Title | Governance, Decision & Issue Management — Standard Operating Procedure |
| Document Owner | FCRM Enterprise Risk Assessment Reporting Team (MCC Team) |
| Effective Date | June 2026 |
| Version | 1.0 |
| Target Audience | 1LOD, 2LOD, 3LOD (Internal Audit), and Regulatory Reviewers |
| System of Record | Jira (FY25 RA CYCLE - DATA) + RAID Log + SharePoint |

1.  Purpose

This SOP defines the mandatory governance, decision-logging, and issue-management procedures for the FY2025 Anti-Money Laundering (AML) and Sanctions Enterprise Risk Assessment (RA) process. It ensures that:

every business-logic, scoping, and methodology decision is captured and traceable;

every issue, blocker, or data-quality failure is logged, classified, escalated, and resolved through a controlled path; and

data gaps below threshold are formally risk-accepted by stakeholders rather than silently suppressed, so the Inherent Risk rating of an Assessable Unit (AU) is never artificially lowered.

Governance rule: All business logic and methodology decisions must be formally captured in Jira. Unlogged out-of-band decisions cannot be considered authoritative and will be flagged as audit findings.

2.  Scope

This SOP applies to all governance activity performed by the MCC Team across the RA delivery cycle, covering:

Business logic, scoping, and methodology decisions

Assumptions, default thresholds, and proxy-data choices

Issues, blockers, and data-quality failures

Severity classification and escalation

Resolution and unblocking

Risk acceptance of data below the 95% data-quality threshold

Decommissioning of retired metrics, AUs, or Work Packages

Out of scope: Decisions owned by First Line (1LOD) business stakeholders, enterprise-level governance outside the RA data-delivery work, and changes to upstream source systems (Rahona, ADIDO).

3.  Key Principles

The following principles govern all decision and issue-management activity:

No decision is authoritative unless it is logged in Jira — out-of-band or verbal decisions are not permitted

Every issue or blocker has both a Jira BLOCKED state and a corresponding RAID log entry

Severity is classified consistently (P1 / P2 / P3) and drives escalation urgency

Escalation follows the defined matrix; verbal escalations alone are not sufficient for audit

An issue is considered resolved only when it is marked Closed in the RAID log

Data below the 95% threshold is formally risk-accepted by key stakeholders — never silently dropped

Retired scope is transitioned (NO LONGER REQUIRED / NOT APPLICABLE), not deleted — historical traceability is preserved

4.  Process Steps

The governance process consists of eight sequential steps. Steps 1–4 are owned by the Decision & Issue owner; Steps 5–8 are owned by the Escalation & Resolution owner.

| # | Step Name | Jira State | Inputs | Actions | Outputs | Appr. |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Decision Logging | BUSINESS LOGIC DESIGN DEF → BUSINESS LOGIC SEMANTIC | Business logic discussions, methodology decisions | Capture all business logic, scoping, and methodological decisions in Jira. No out-of-band decisions. | Jira ticket with full decision notes | No |
| 2 | Assumption Tracking | METRIC DEFINITION CLARIFICATION → BAU CDE DOCUMENTATION | Ambiguous requirements, proxy data, default thresholds | Formally document ambiguities, default thresholds, and proxy-data assumptions; resolve in the relevant Jira state. | Jira ticket, assumption log | No |
| 3 | Issue Logging | BLOCKED | Identified blockers, data issues, QA failures | If a metric cannot proceed (upstream QA failure, missing source), transition the ticket to BLOCKED and create a RAID log entry. | RAID log entry, BLOCKED Jira ticket | No |
| 4 | Severity Assessment | BLOCKED | Logged issues in RAID | Classify each issue: P1 = critical data gaps, P2 = systemic failures, P3 = localized logic discrepancies. Priority sets escalation urgency. | Severity classification (P1/P2/P3) in RAID log | No |
| 5 | Escalation Pathways | BLOCKED | Unresolved BLOCKED issues beyond SLA | Apply the escalation matrix: Developer → Team Lead → Project Manager → Business Stakeholders / 2LOD. Categorize blocker type. | Escalation record, Jira comments, 2LOD notification | No |
| 6 | Resolution & Unblocking | BLOCKED → READY FOR FINAL REVIEW | Resolved issues, RAID log closure | Confirm the issue is Closed in the RAID log; only then transition the Jira ticket off BLOCKED. | RAID log closure record, Jira state transition | Yes |
| 7 | Risk Acceptance | NOT AVAILABLE | Unresolvable issues (data below threshold) | Data below threshold is formally risk-accepted by key stakeholders → NOT AVAILABLE → triggers the higher risk rating for the impacted AU. | NOT AVAILABLE Jira state, risk-acceptance record | Yes |
| 8 | Decommissioning & Sign-Off | NO LONGER REQUIRED / NOT APPLICABLE | Out-of-scope metrics, retired AUs, deprecated Work Packages | Transition retired scope to NO LONGER REQUIRED or NOT APPLICABLE; log in the SOW change log. Preserve historical traceability. | Jira state transition, SOW change log entry | No |

4.1  Step 1 — Decision Logging

All business-logic, scoping, and methodological decisions must be captured in Jira in the FY25 RA CYCLE - DATA project. Initial business rules and metric definitions are formalized while the ticket is in BUSINESS LOGIC DESIGN DEF and BUSINESS LOGIC SEMANTIC states. The decision record must include what was decided, the rationale, who decided it, and the date.

Unlogged out-of-band decisions are not permitted. A decision that exists only in email, chat, or conversation is not authoritative and will be raised as an audit finding.

4.2  Step 2 — Assumption Tracking

Ambiguities in requirements, default thresholds, and proxy-data assumptions must be formally documented and resolved while the ticket is in METRIC DEFINITION CLARIFICATION or BAU CDE DOCUMENTATION state. Each assumption record must state the ambiguity, the assumption made, the basis for it, and the resolution.

4.3  Step 3 — Issue Logging

When a metric cannot proceed — for example due to an upstream QA failure or a missing source file — the Jira ticket must immediately transition to BLOCKED, and a corresponding entry must be captured in the formal RAID Log (Risks, Assumptions, Issues, Dependencies). The RAID entry must describe the issue, the impacted metrics/AUs, and the dependency or root cause where known.

A BLOCKED Jira ticket without a matching RAID log entry is incomplete. Both must exist for the issue to be considered logged.

4.4  Step 4 — Severity Assessment

Every logged issue undergoes standardized severity assessment, which determines escalation urgency:

P1 — Critical data gaps (e.g., a CDE required to close an AU is unavailable)

P2 — Systemic failures (e.g., a fault affecting multiple metrics or AUs)

P3 — Localized logic discrepancies (e.g., a single-metric logic issue with limited impact)

The severity classification is recorded against the issue in the RAID log.

4.5  Step 5 — Escalation Pathways

When an issue cannot be resolved within its SLA, it is escalated through the structured matrix:

Developer → Team Lead → Project Manager → Business Stakeholders / 2LOD

Each escalation must categorize the blocker type and be recorded in the Jira ticket comments and the RAID log. P1 issues are escalated immediately.

All escalations must be documented in the Jira ticket comments and the RAID log — verbal escalations alone are not sufficient for audit purposes.

4.6  Step 6 — Resolution & Unblocking

An issue is considered resolved only when it is marked Closed in the RAID log. Only then may the Jira ticket leave the BLOCKED state and proceed toward READY FOR FINAL REVIEW.

Approval required: A Team Lead or Product Owner confirms the RAID closure before the ticket is unblocked. The approver must be independent of the person who raised the issue.

4.7  Step 7 — Risk Acceptance

Where an issue cannot be resolved — most commonly when data quality is below the 95% threshold and the business cannot provide the data — the gap is formally risk-accepted by all key stakeholders. The ticket transitions to NOT AVAILABLE, which triggers the higher risk rating for the impacted AU. This is a deliberate control: routing an unresolved data gap to NOT AVAILABLE prevents the artificial suppression of Inherent Risk that would occur if the metric were simply dropped.

Approval required: Risk acceptance must be signed off by all key stakeholders, including the Product Owner and 2LOD. The risk-acceptance record is an audit artifact.

4.8  Step 8 — Decommissioning & Sign-Off

Metrics, AUs, or Work Packages that are retired or no longer applicable must be transitioned to NO LONGER REQUIRED or NOT APPLICABLE in Jira, and the change logged in the SOW change log. Retired scope is never deleted, so historical traceability is preserved for audit.

5.  Jira Workflow States

The following Jira states are used in the governance process:

| Jira State | Meaning in Governance Context |
| --- | --- |
| BUSINESS LOGIC DESIGN DEF | Business-logic / scoping / methodology decision raised and documented. |
| BUSINESS LOGIC SEMANTIC | Semantic refinement of a logged business-logic decision. |
| METRIC DEFINITION CLARIFICATION | An ambiguity or assumption is being formally clarified and recorded. |
| BAU CDE DOCUMENTATION | A BAU CDE assumption / definition is documented. |
| BLOCKED | Issue raised; metric cannot proceed. Requires a matching RAID log entry. |
| READY FOR FINAL REVIEW | Issue resolved and RAID-closed; ticket has left BLOCKED. |
| NOT AVAILABLE | Data below threshold, formally risk-accepted. Triggers a higher AU risk rating. |
| NO LONGER REQUIRED | Scope retired / cancelled. Historical traceability preserved. |
| NOT APPLICABLE | Metric / AU is not applicable to the unit (e.g., CTR/LCTR for a unit with no cash in/out). |

6.  Roles & Responsibilities

| Role | Responsibilities |
| --- | --- |
| Decision & Assumption Owner | Capture all decisions and assumptions in Jira in the correct states (Steps 1–2). |
| Issue / RAID Owner | Log issues to BLOCKED + RAID, classify severity P1/P2/P3 (Steps 3–4). |
| Escalation Owner | Drive the escalation matrix; record escalations and 2LOD notification (Step 5). |
| Resolution Owner | Confirm RAID closure and unblock the ticket (Step 6). |
| Approver | Team Lead or Product Owner confirms unblocking (Step 6); key stakeholders incl. Product Owner and 2LOD sign off risk acceptance (Step 7). Approver is independent of the issue raiser. |
| Developer | Raise issues promptly with full detail; provide information needed to resolve. |

7.  Evidence & Audit Trail

The following artifacts constitute the audit evidence that this governance process was followed:

| Artifact | What It Proves | Where Stored |
| --- | --- | --- |
| Jira decision tickets | Decisions were logged in-band with full notes | Jira — FY25 RA CYCLE - DATA |
| Assumption log | Ambiguities and proxy assumptions were formally recorded | Jira — METRIC DEFINITION CLARIFICATION |
| RAID log entries | Issues were logged with impact and dependency detail | RAID Log (Jira) |
| BLOCKED Jira tickets | Blocked metrics were flagged and could not silently proceed | Jira — ticket state history |
| Severity classification | Issues were prioritized consistently (P1/P2/P3) | RAID Log |
| Escalation records + 2LOD notification | Unresolved issues were escalated through the matrix | Jira comments; RAID Log |
| RAID closure records | Issues were formally resolved before unblocking | RAID Log; Jira state transition |
| Risk-acceptance record | Below-threshold data was formally accepted by stakeholders | Jira NOT AVAILABLE state; sign-off |
| Decommissioning transitions + SOW change log | Retired scope was transitioned, not deleted | Jira; SOW v1.32 change log |

8.  Constraints, Assumptions & Escalation

8.1  Constraints

A BLOCKED ticket may not leave the BLOCKED state until the corresponding RAID item is Closed

Risk acceptance cannot be self-approved — it requires sign-off from key stakeholders including 2LOD

Retired metrics/AUs must be transitioned to NO LONGER REQUIRED or NOT APPLICABLE, never deleted

A decision or assumption that is not in Jira is not authoritative

8.2  Escalation Path

If an issue is blocked or cannot be resolved within SLA:

Developer raises the BLOCKED ticket and RAID log entry

Team Lead notified — drives resolution within the severity SLA

Project Manager engaged if unresolved after Team Lead review

Business Stakeholders / 2LOD notified for systemic (P1) issues

All escalations must be documented in the Jira ticket comments and the RAID log — verbal escalations alone are not sufficient for audit purposes.

9.  Related Documents

QA & Governance Standard SOP v2.1 — SharePoint: 02 - Validation & QA

Change Management and Version Control SOP v1.1 — SharePoint: 06 - Change Management

Delivery Process SOP v2.1 — SharePoint: 01 - Delivery Process

Data Sourcing & Lineage SOP v2.1 — SharePoint: 03 - Data Sourcing & Lineage

Statement of Work v1.32 (Richard Ng) — SharePoint: 00 - Audit Navigation

RAID Log — Jira (FY25 RA CYCLE - DATA)

Audit Summary v1.3 — SharePoint: 00 - Audit Navigation