## Process Inventory
FCRM Risk Assessment FY2025 — Process Inventory
Complete process detail: inputs, actions, outputs, approvals, Jira states, tools, and SOP references ¦ Internal ¦ April 2026
Process | Sub-Process / Control Area | Step # | Step Name | Owner | Inputs | Actions / Description | Outputs / Deliverables | Approval Required? | Approver | Jira Workflow State | Tool / System | SOP Reference | Notes
Delivery Process | Requirement Definition; Data Acquisition; Logic Dev; Change Mgmt; Deployment; Delivery; BAU | 0 | Intake Request | Amandeep | Business requirements, CDE list, AU scope | Raise intake request with purpose, AUs in scope, expected output and timelines. Identify Critical Data Elements (ERA/FCRM/Business). Perform initial review (1a/1b/Bas). IR review and challenge with core business. | Jira intake ticket, CDE list, initial review record | Yes | Team Lead / Business | BUSINESS LOGIC DESIGN DEF | Jira | Delivery Process SOP v1.2
|  | 1 | Scope / Requirement Definition | Amandeep | Intake ticket, SOW, AU list | Identify and capture Critical Data Elements required to close RA cycle for FY2025. Define scope boundaries. Business logic and queries approved by First Line. | Scope & Requirements Document, SOW reference | Yes | AVP+ | BUSINESS LOGIC DESIGN DEF | SharePoint | Delivery Process SOP v1.2
|  | 2 | Data Acquisition | Amandeep | Approved scope, Rahona/ADIDO access, PIA approvals | Source data from Rahona (20 sources) and ADIDO (73 sources). Load to Canada Analytical Zone (CA AZ). Validate data integrity and completeness post-extraction. | Extracted dataset files (.csv/.parquet) in CA AZ, extraction scripts, extraction validation report | No |  | DATA SOURCE(S) IDENTIFIED → DATA PROVISIONED IN AZ | Rahona / ADIDO / CA AZ | Delivery Process SOP v1.2
|  | 3 | Logic Development (Build) | Karthik | Extracted datasets in CA AZ, metric definitions, business logic approved by 1LOD | Write Python-SQL queries, joins, filters, aggregations. Define and generate output. Document logic and transformations. | Python-SQL code in Git, Jira ticket in BUILD IN PROGRESS, transformation logic documentation | No |  | BUILD IN PROGRESS (PART) → BUILD IN PROGRESS (FULL) | GitHub / CA AZ | Delivery Process SOP v1.2
|  | 4 | Technical Specifications (Build) | Karthik | Build code, metric definitions, lineage requirements | Document technical specifications including transformation logic, field-level mapping, data lineage from source to output. | Tech spec document, source-to-report mapping, field-level lineage | No |  | BUILD IN PROGRESS (FULL) | SharePoint / GitHub | Delivery Process SOP v1.2
|  | 5 | Output Validation | Karthik | Build outputs, expected metric values, validation criteria | Validate output against expected results. Cross-check with source data. Verify format and structure meet regulatory requirements. | Output validation report, reconciliation results | No |  | BUILD COMPLETE | SharePoint | QA & Governance SOP v2.1
|  | 6 | Approval | Karthik | Validated outputs, completed validation checklist | Obtain PO Concurrence. Transition Jira to PO APPROVED. Reviewers must be independent of preparer. Approver must be AVP or higher. | Jira ticket in PO APPROVED state, approval record | Yes | AVP+ | PO CONCURRENCE → PO APPROVED | Jira | Approvals Document v1.1
|  | 7 | Deployment | Karthik | Approved outputs, deployment checklist | Deploy metric outputs to production. Record deployment details. Confirm successful release. | Deployment log, release record | Yes | Team Lead | PO APPROVED | Jira / SharePoint | Delivery Process SOP v1.2
|  | 8 | Delivery / Document Output | Karthik | Deployed outputs | Deliver final metric outputs. Document results. Store in SharePoint. Confirm delivery with stakeholders. | Final output files, delivery confirmation, output documentation | No |  | PO APPROVED | SharePoint / CA AZ | Delivery Process SOP v1.2
Validation & Quality Assurance | DQ Checks; Reconciliation; Peer Review; Output Verification | 1 | Validation Planning | Priyanshi | Scope document, metric definitions, AU list | Define validation scope (datasets, systems, outputs). Identify key controls and risk areas. Establish timelines and milestones. Assign roles and responsibilities. Document methodology and acceptance criteria. | Validation Plan Document, Risk Assessment Matrix | No |  | BUSINESS LOGIC DESIGN DEF | SharePoint | QA & Governance SOP v2.1
|  | 2 | Data Quality Checks | Priyanshi | Extracted datasets in CA AZ | Completeness: no missing/null critical fields. Accuracy: validate against source systems (95% threshold). Consistency: cross-check values. Uniqueness: identify duplicates. Timeliness: data up-to-date. Methods: automated scripts + manual sampling. | DQ check results, profiling reports, issue log | No |  | DATA PROVISIONED IN AZ | CA AZ / SharePoint | QA & Governance SOP v2.1
|  | 3 | Reconciliation | Priyanshi | Source data counts, processed data counts | Reconcile record counts between source and processed data. Validate key financial metrics. Identify and investigate variances. Document all reconciliation results. | Reconciliation reports, variance analysis logs | No |  | DATA PROVISIONED IN AZ | SharePoint | QA & Governance SOP v2.1
|  | 4 | Reasonability Analysis | Priyanshi | Metric outputs, historical data, expected thresholds | Assess whether AML outputs are logical and within expected thresholds. Trend analysis. Comparison with historical data. Outlier detection. Threshold validation. Check for sudden spikes/drops. | Trend analysis output, outlier detection log, threshold validation report | No |  | BUILD IN PROGRESS (FULL) | SharePoint | QA & Governance SOP v2.1
|  | 5 | Peer Review | Sujai | Build outputs, methodology documentation | Assign reviewer independent of preparer. Review methodology, calculations, and outputs. Validate assumptions and logic. Document review comments and resolutions. Privacy compliance check (PIA BUILD → WITH PRIVACY TEAM → PIA APPROVED). | Peer review sign-off, review comments log, AU REVIEW APPROVAL Jira state | Yes | Independent reviewer (not preparer) | AU REVIEW APPROVAL | SharePoint / Jira | QA & Governance SOP v2.1
|  | 6 | Output Verification | Sujai | Final metric outputs, format requirements | Verify output format and structure. Validate key fields and calculations. Cross-check with source and intermediate data. Ensure regulatory compliance. Execution gating: cannot proceed until Steps 1–5 cleared. | Output verification report, format compliance log | No |  | BUILD COMPLETE | SharePoint | Output Validation Document v1.1
|  | 7 | Issue Logging | Sujai | Identified issues from any prior step | Log issues in RAID log immediately. Transition Jira to BLOCKED state. Categorize severity (P1=critical data gap, P2=systemic failure). Assign ownership and due dates. Track resolution status. Maintain audit trail. | RAID log entry, Jira BLOCKED ticket with full issue detail | No |  | BLOCKED | Jira / SharePoint | QA & Governance SOP v2.1
|  | 8 | Sign-Off & Approval | Sujai | Completed validation checklist, all issues resolved or accepted | Ensure all validation steps are completed. Confirm all issues resolved or formally risk-accepted. Obtain approvals (AVP+). Reviewer cannot be same as preparer. Transition Jira to PO CONCURRENCE → PO APPROVED. | Signed approval record, final validation report | Yes | AVP+ | PO CONCURRENCE → PO APPROVED | SharePoint / Jira | Approvals Document v1.1
Data Sourcing & Lineage | Source Identification; Access; Extraction; Lineage; Retention | 1 | Source Identification | Hua | Business requirements, metric definitions, SOW | Review business and regulatory requirements. Create Master_Data_source_FY2025.xlsx to identify all relevant data sources per metric. Collaborate with business stakeholders. Document system names, tables, owners, data attributes. | Master_Data_source_FY2025.xlsx, source identification log | No |  | BUSINESS LOGIC DESIGN DEF | SharePoint | Data Sourcing & Lineage v1.0
|  | 2 | Access Enablement | Hua | Identified data sources, organizational PIA guidelines | Initiate Privacy Impact Assessment (PIA) process for each data source. Submit access requests. Track and follow up on access approvals. Maintain records of all access permissions and compliance checks. | PIA approval records, access request forms, access approval log | Yes | Privacy Team / Data Owner | DATA SOURCE(S) IDENTIFIED | SharePoint | Data Sourcing & Lineage v1.0
|  | 3 | Data Extraction | Hua | Approved access credentials, Master Data Source Sheet | Use approved credentials to connect to Rahona (20 sources) and ADIDO (73 sources). Extract relevant data fields per requirements. Store in CA AZ. Validate integrity and completeness post-extraction. | Extracted dataset files (.csv/.parquet), extraction scripts, extraction validation report | No |  | DATA PROVISIONED IN AZ | Rahona / ADIDO / CA AZ | Data Sourcing & Lineage v1.0
|  | 4 | Data Understanding | Subham | Extracted datasets in CA AZ | Create database views or data models. Profile datasets for completeness, accuracy, consistency. Document data definitions, data types, key attributes. Identify and address data quality issues. | Data profiling reports, data dictionary / metadata documentation, data quality assessment report | No |  | DATA PROVISIONED IN AZ | CA AZ / SharePoint | Data Sourcing & Lineage v1.0
|  | 5 | Lineage Documentation | Subham | Extraction scripts, transformation logic, metric definitions | Build queries producing result values for each metric. Map complete data journey from extraction to reporting including all transformations and business logic applied. Maintain lineage diagrams. Ensure accessible for audit. | Data lineage diagrams, transformation logic documentation, lineage register | No |  | BUILD IN PROGRESS (FULL) | SharePoint / GitHub | Data Sourcing & Lineage v1.0
|  | 6 | Refresh Management | Raghul | CA AZ datasets, business/audit refresh requests | Data pulled for RA FY2025 and refreshed at source system level on-demand (not fixed schedule). RA team extracts and stores in CA AZ. Document all refresh activities. Validate data integrity after each refresh. | Refresh activity log, extracted dataset files (refreshed), refresh validation reports | No |  | DATA PROVISIONED IN AZ | CA AZ / SharePoint | Data Sourcing & Lineage v1.0
|  | 7 | Data Retention | Raghul | CA AZ datasets, organizational retention policies | Currently no defined retention policy — datasets stored in CA AZ without a defined retention period. Periodically review organizational and regulatory requirements. Update documentation if requirements change. | Data retention statement, retention policy reference (if applicable), retention/disposal log | No |  | N/A | SharePoint | Data Sourcing & Lineage v1.0
Governance & Issue Management | Decision Logging; Assumptions; Issue Mgmt; Escalation; Risk Acceptance | 1 | Decision Logging | Patty | Business logic discussions, methodology decisions | All business logic, scoping, and methodological decisions must be captured in Jira. Unlogged out-of-band decisions are not permitted. Initial business rules and metric definitions formalized while ticket is in BUSINESS LOGIC DESIGN DEF and BUSINESS LOGIC SEMANTIC states. | Jira ticket in BUSINESS LOGIC DESIGN DEF state with full decision notes | No |  | BUSINESS LOGIC DESIGN DEF / BUSINESS LOGIC SEMANTIC | Jira | QA & Governance SOP v2.1
|  | 2 | Assumption Tracking | Patty | Ambiguous requirements, proxy data, default thresholds | Ambiguities in requirements, default thresholds, or proxy data assumptions must be formally documented. Resolved while ticket is in METRIC DEFINITION CLARIFICATION or BAU CDE DOCUMENTATION state. | Jira ticket in METRIC DEFINITION CLARIFICATION state, assumption log | No |  | METRIC DEFINITION CLARIFICATION / BAU CDE DOCUMENTATION | Jira | QA & Governance SOP v2.1
|  | 3 | Issue Logging | Patty | Identified blockers, data issues, QA failures | If metric cannot proceed due to upstream QA failure or missing source file, Jira ticket must immediately transition to BLOCKED. Corresponding entry captured in formal RAID Log. | RAID log entry, Jira BLOCKED ticket with issue detail | No |  | BLOCKED | Jira / SharePoint | QA & Governance SOP v2.1
|  | 4 | Severity Assessment | Patty | Logged issues in RAID | Issues undergo standardized severity assessment: P1 = critical data gaps, P2 = systemic failures, P3 = localized logic discrepancies. Priority determines escalation urgency and SLA. | Severity classification (P1/P2/P3) in RAID log | No |  | BLOCKED | Jira / SharePoint | QA & Governance SOP v2.1
|  | 5 | Escalation Pathways | Tom | Unresolved BLOCKED issues beyond SLA | When issue cannot be resolved within SLAs, use structured escalation matrix: Developer → Team Lead → Project Manager → Business Stakeholders / 2LOD. Escalations must clearly categorize blocker type. | Escalation record, Jira comments showing escalation chain, 2LOD notification | No |  | BLOCKED | Jira / Email | QA & Governance SOP v2.1
|  | 6 | Resolution & Unblocking | Tom | Resolved issues, RAID log closure | Issue is formally considered resolved only when marked 'Closed' in RAID log. Only then may the Jira ticket leave BLOCKED state and proceed toward READY FOR FINAL REVIEW. | RAID log closure record, Jira state transition off BLOCKED | Yes | Team Lead | BLOCKED → READY FOR FINAL REVIEW | Jira / SharePoint | QA & Governance SOP v2.1
|  | 7 | Risk Acceptance | Tom | Unresolvable issues, data below 95% threshold | If data completeness falls below required thresholds and cannot be remediated before reporting deadlines, must be formally risk-accepted by all key stakeholders. Metric ticket transitioned to NOT AVAILABLE. Triggers default to higher risk rating for impacted AU. | Risk acceptance record, metric in NOT AVAILABLE Jira state, stakeholder sign-off | Yes | AVP+ / 2LOD | NOT AVAILABLE | SharePoint / Jira | QA & Governance SOP v2.1
|  | 8 | Decommissioning | Tom | Out-of-scope metrics, retired AUs, deprecated work packages | Metrics, AUs, or Work Packages retired or no longer applicable must be transitioned to NO LONGER REQUIRED or NOT APPLICABLE Jira states. Ensures historical traceability. | Jira state: NO LONGER REQUIRED or NOT APPLICABLE, SOW scope change log entry | No |  | NO LONGER REQUIRED / NOT APPLICABLE | Jira / SharePoint | QA & Governance SOP v2.1
Access Control & Security | PIAs; Access Control; DEV vs PROD; Periodic Reviews; Retention | 1 | PIA Initiation | Hua | Data source list, privacy requirements | Initiate Privacy Impact Assessment for each data source requiring access to personal or sensitive data. Follow organizational PIA guidelines. Coordinate with Privacy Team. PIA BUILD → WITH PRIVACY TEAM → PIA APPROVED. | PIA documentation, PIA Jira state transitions | Yes | Privacy Team | PIA BUILD → WITH PRIVACY TEAM → PIA APPROVED | SharePoint / Jira | Access Control SOP
|  | 2 | Access Request & Approval | Hua | Approved PIA, system access requirements | Submit access requests for all required systems and datasets. Track and follow up on approvals. Maintain records of all access permissions and compliance checks for audit purposes. | Access request forms, access approval records, access approval log | Yes | Data Owner / IT Security | DATA SOURCE(S) IDENTIFIED | SharePoint | Access Control SOP
|  | 3 | Access Control Matrix | TBD | Approved access records | Maintain access control matrix documenting who has access to which systems, datasets, and environments. Document segregation of duties. | Access control matrix, segregation of duties documentation | No |  | N/A | SharePoint | Access Control SOP
|  | 4 | DEV vs PROD Separation | TBD | Environment configuration | Maintain strict separation between DEV and PROD environments. No production data in DEV without approval. Document environment boundaries and access controls. | DEV/PROD separation evidence, environment access records | No |  | N/A | SharePoint | Access Control SOP
|  | 5 | Periodic Access Review | TBD | Current access records | Conduct periodic reviews of all access permissions. Remove stale or unnecessary access. Document review outcomes and maintain audit trail of access changes. | Periodic access review log, attestation records | Yes | Team Lead / Security | N/A | SharePoint | Access Control SOP
Change Management | Change Tickets; Git Version Control; Approvals; Deployment; Rollback | 1 | Change Request | TBD | Proposed logic/scope change, business justification | Raise Jira change ticket before any modification to metric logic, data sources, or scope. Document change description, impacted metrics, AUs, and rationale. | Jira change ticket with full change description | No |  | BUSINESS LOGIC DESIGN DEF | Jira | Change Management SOP
|  | 2 | Impact Assessment | TBD | Change ticket, metric dependency map | Assess impact of proposed change on affected metrics, AUs, downstream outputs. Document assessment in Jira ticket. Identify any re-testing or re-validation required. | Impact assessment notes in Jira ticket | No |  | BUSINESS LOGIC DESIGN DEF | Jira | Change Management SOP
|  | 3 | Change Approval | TBD | Impact-assessed change ticket | Obtain approval for change before implementation. Approver must be independent of change requester. Approval logged in Jira ticket. | Approval sign-off on Jira change ticket | Yes | Team Lead / AVP+ | PO CONCURRENCE | Jira | Change Management SOP
|  | 4 | Version Control | TBD | Approved change, existing codebase | All code changes committed to Git with meaningful commit messages referencing Jira ticket ID. Pull request / merge record maintained. Full version history preserved. | Git commit history, PR/merge record, branch history | No |  | BUILD IN PROGRESS | GitHub | Change Management SOP
|  | 5 | Deployment & Rollback | TBD | Approved, version-controlled change | Deploy change to production following standard deployment process. Document deployment. Maintain rollback procedures in case of failure. Archive prior version outputs. | Deployment log, release notes, rollback procedure | Yes | Team Lead | PO APPROVED | SharePoint / GitHub | Change Management SOP
|  | 6 | Scope Change Logging | Richard Ng | Approved scope change, SOW | All scope changes logged in SOW (v1.32, updated weekly). Update cadence: Thursday → Friday → Monday → Tuesday. References Jira Kanban updates. | SOW weekly change log entry (v1.32), scope change record | No |  | N/A | SharePoint | Change Management SOP

## Evidence Tracker
FCRM Risk Assessment FY2025 — Evidence Tracker
Maps each process step to required evidence, artifact locations, status, and audit readiness ¦ Internal ¦ April 2026
Process | Step # | Step Name | Owner | Expected Evidence / Artifact | Artifact Name / File | SharePoint / Jira Location | Status | Jira Ticket(s) | Last Verified | Verified By | Gap / Notes | Priority | Due Date | SOP Reference | Audit Ready?
Delivery Process | 0 | Intake Request | Amandeep | Jira ticket, CDE documentation |  |  | Missing | [6 empty] | Delivery Process SOP v1.2 | No
| 1 | Scope / Requirement Definition | Amandeep | Scope & Requirements Document v1.2 |  |  | Missing | [6 empty] | Delivery Process SOP v1.2 | No
| 2 | Data Acquisition | Amandeep | Extracted files, extraction scripts |  |  | Missing | [6 empty] | Delivery Process SOP v1.2 | No
| 3 | Logic Development (Build) | Karthik | Git commit history, code files |  |  | Missing | [6 empty] | Delivery Process SOP v1.2 | No
| 4 | Technical Specifications (Build) | Karthik | Technical specification document |  |  | Missing | [6 empty] | Delivery Process SOP v1.2 | No
| 5 | Output Validation | Karthik | Output validation report |  |  | Missing | [6 empty] | QA & Governance SOP v2.1 | No
| 6 | Approval | Karthik | Jira state transition, approval record |  |  | Missing | [6 empty] | Approvals Document v1.1 | No
| 7 | Deployment | Karthik | Deployment log |  |  | Missing | [6 empty] | Delivery Process SOP v1.2 | No
| 8 | Delivery / Document Output | Karthik | Output files, delivery confirmation |  |  | Missing | [6 empty] | Delivery Process SOP v1.2 | No
Validation & Quality Assurance | 1 | Validation Planning | Priyanshi | Validation Plan Document |  |  | Missing | [6 empty] | QA & Governance SOP v2.1 | No
| 2 | Data Quality Checks | Priyanshi | DQ check output files, profiling reports |  |  | Missing | [6 empty] | QA & Governance SOP v2.1 | No
| 3 | Reconciliation | Priyanshi | Reconciliation reports, variance logs |  |  | Missing | [6 empty] | QA & Governance SOP v2.1 | No
| 4 | Reasonability Analysis | Priyanshi | Reasonability analysis report |  |  | Missing | [6 empty] | QA & Governance SOP v2.1 | No
| 5 | Peer Review | Sujai | Peer review sign-off document |  |  | Missing | [6 empty] | QA & Governance SOP v2.1 | No
| 6 | Output Verification | Sujai | Output verification report |  |  | Missing | [6 empty] | Output Validation Document v1.1 | No
| 7 | Issue Logging | Sujai | RAID log, Jira BLOCKED ticket |  |  | Missing | [6 empty] | QA & Governance SOP v2.1 | No
| 8 | Sign-Off & Approval | Sujai | Signed approval record |  |  | Missing | [6 empty] | Approvals Document v1.1 | No
Data Sourcing & Lineage | 1 | Source Identification | Hua | Master Data Source Sheet |  |  | Missing | [6 empty] | Data Sourcing & Lineage v1.0 | No
| 2 | Access Enablement | Hua | PIA records, access approval log |  |  | Missing | [6 empty] | Data Sourcing & Lineage v1.0 | No
| 3 | Data Extraction | Hua | Extracted files, extraction scripts |  |  | Missing | [6 empty] | Data Sourcing & Lineage v1.0 | No
| 4 | Data Understanding | Subham | Data profiling reports, data dictionary |  |  | Missing | [6 empty] | Data Sourcing & Lineage v1.0 | No
| 5 | Lineage Documentation | Subham | Lineage diagrams, transformation logic doc |  |  | Missing | [6 empty] | Data Sourcing & Lineage v1.0 | No
| 6 | Refresh Management | Raghul | Refresh activity log, refresh validation report |  |  | Missing | [6 empty] | Data Sourcing & Lineage v1.0 | No
| 7 | Data Retention | Raghul | Data retention statement |  |  | Missing | [6 empty] | Data Sourcing & Lineage v1.0 | No
Governance & Issue Management | 1 | Decision Logging | Patty | Jira decision tickets |  |  | Missing | [6 empty] | QA & Governance SOP v2.1 | No
| 2 | Assumption Tracking | Patty | Jira assumption tickets |  |  | Missing | [6 empty] | QA & Governance SOP v2.1 | No
| 3 | Issue Logging | Patty | RAID log, Jira BLOCKED ticket |  |  | Missing | [6 empty] | QA & Governance SOP v2.1 | No
| 4 | Severity Assessment | Patty | RAID log with severity classification |  |  | Missing | [6 empty] | QA & Governance SOP v2.1 | No
| 5 | Escalation Pathways | Tom | Jira escalation comments, email records |  |  | Missing | [6 empty] | QA & Governance SOP v2.1 | No
| 6 | Resolution & Unblocking | Tom | RAID log closure, Jira state history |  |  | Missing | [6 empty] | QA & Governance SOP v2.1 | No
| 7 | Risk Acceptance | Tom | Risk acceptance document, Jira state |  |  | Missing | [6 empty] | QA & Governance SOP v2.1 | No
| 8 | Decommissioning | Tom | Jira state transition, SOW change log |  |  | Missing | [6 empty] | QA & Governance SOP v2.1 | No
Access Control & Security | 1 | PIA Initiation | Hua | PIA documentation |  |  | Missing | [6 empty] | Access Control SOP | No
| 2 | Access Request & Approval | Hua | Access request forms, approval records |  |  | Missing | [6 empty] | Access Control SOP | No
| 3 | Access Control Matrix | TBD | Access control matrix |  |  | Missing | [6 empty] | Access Control SOP | No
| 4 | DEV vs PROD Separation | TBD | Environment separation documentation |  |  | Missing | [6 empty] | Access Control SOP | No
| 5 | Periodic Access Review | TBD | Access review log |  |  | Missing | [6 empty] | Access Control SOP | No
Change Management | 1 | Change Request | TBD | Jira change ticket |  |  | Missing | [6 empty] | Change Management SOP | No
| 2 | Impact Assessment | TBD | Jira ticket impact notes |  |  | Missing | [6 empty] | Change Management SOP | No
| 3 | Change Approval | TBD | Jira approval record |  |  | Missing | [6 empty] | Change Management SOP | No
| 4 | Version Control | TBD | Git commit history |  |  | Missing | [6 empty] | Change Management SOP | No
| 5 | Deployment & Rollback | TBD | Deployment log, rollback doc |  |  | Missing | [6 empty] | Change Management SOP | No
| 6 | Scope Change Logging | Richard Ng | SOW change log |  |  | Missing | [6 empty] | Change Management SOP | No

## Summary Dashboard
Evidence Tracker — Summary Dashboard
Auto-updates as you fill in Status column in the Evidence Tracker sheet
Process Area | Total Steps | Exists | Partial | Missing | % Complete
Delivery Process | 9
Validation & Quality Assurance | 8
Data Sourcing & Lineage | 7
Governance & Issue Management | 8
Access Control & Security | 5
Change Management | 6
TOTAL
KEY PROJECT STATS (FY2025)
Total Work Packages |  |  |  | 4
Total Metric Definitions |  |  |  | 86
Total Assessable Units (AUs) |  |  |  | 35
Total Metric Instances |  |  |  | 2,240
Jira — BUILD COMPLETE |  |  |  | 754
Jira — BLOCKED (active) |  |  |  | 49
RAID Log Items |  |  |  | 137
Rahona Data Sources |  |  |  | 20
ADIDO Data Sources |  |  |  | 73

## Resourcing Team
FY2025 Risk Assessment — Resourcing & Process Ownership
Maps team members to process ownership and step assignments
Process | Sub-Process / Control Area | Process Steps | Resources | Notes
Delivery Process | Requirement Definition; Data Acquisition; Logic Dev; Change Mgmt; Deployment; Delivery; BAU | 0. Intake Request 1. Scope / Requirement Definition 2. Data Acquisition 3. Logic Development (Build) 4. Technical Specifications (Build) 5. Output Validation 6. Approval 7. Deployment 8. Output / Document | Amandeep: Steps 0–4 Karthik: Steps 5–8
Validation & Quality Assurance | DQ Checks; Reconciliation; Peer Review; Output Verification | 1. Validation Planning 2. Data Quality Checks 3. Reconciliation 4. Reasonability Analysis 5. Peer Review 6. Output Verification 7. Issue Logging 8. Sign-Off & Approval | Priyanshi: Steps 1–4 Sujai: Steps 5–8
Data Sourcing & Lineage | Source Identification; Access; Extraction; Lineage; Retention | 1. Source Identification 2. Access Enablement 3. Data Extraction 4. Data Understanding 5. Lineage Documentation 6. Refresh Management 7. Data Retention | Hua: Steps 1–3 Subham: Steps 4–5 Raghul: Steps 6–7
Governance & Issue Management | Decision Logging; Assumptions; Issue Mgmt; Escalation; Risk Acceptance | 1. Decision Logging 2. Assumption Tracking 3. Issue Logging 4. Severity Assessment 5. Escalation Pathways 6. Resolution & Unblocking 7. Risk Acceptance 8. Decommissioning | Patty: Steps 1–4 Tom: Steps 5–8
Access Control & Security | PIAs; Access Control Matrix; DEV vs PROD; Periodic Reviews | 1. PIA Initiation 2. Access Request & Approval 3. Access Control Matrix 4. DEV vs PROD Separation 5. Periodic Access Review | Hua: Steps 1–2 TBD: Steps 3–5 | ⚠ Owners TBD — confirm with team leads
Change Management | Change Tickets; Git Version Control; Approvals; Deployment; Rollback | 1. Change Request 2. Impact Assessment 3. Change Approval 4. Version Control 5. Deployment & Rollback 6. Scope Change Logging | TBD: Steps 1–5 Richard Ng: Step 6 | ⚠ Owners TBD — confirm with team leads